## Sheet1
WHAT NEEDS TO BE DONE? | WHO IS GOING TO DO IT? | WHEN MUST THIS BE DONE BY?
future deliverables document | EVERYONE | 2017-02-21
email Bob about missing data | Atefeh
upload new future deliverables document so Buerkle can see it | Nathan
Finish translating Bob's code into Jags | Abby, Atefeh, Nathan, Katie | 2017-02-28
figure out StreamMetabolizer simulation stuff | Daniel, Nicholas
figure out GitHub/ issues to do list thing | EVERYONE
Determine appropriate distributions for priors, parameters, hyperparameters, etc. | Katie
Be able to write out likelihood function | Katie
Upload how do do shit in git doc | Daniel
view metadata on wyocourses and figure out how to incorporate into JAGS | Abby
transfer this list to the github wiki | Daniel?
code new model that incorporates variable flow rate | Abby, Katie, Nathan | 2017-03-07
Test Bob's constant flow model with simulated data from Stream Metabolizer | Daniel, Nick, Atefeh
Summarize results of testing Bob's constant flow model | Daniel, Nick, Atefeh
SPRING BREAK! (catch up on anything we are running behind on) | EVERYONE | 2017-03-14
Test new variable flow model with simulated data from Stream Metabolizer | Abby, Katie, Nathan | 2017-03-21
Summarize findings of simulated data test on new variable flow model | Abby, Katie, Nathan
Start outlining interim report (incorporate findings of test on Bob's model) | Daniel, Nick, Atefeh
Quantify discrepancy between the two models | EVERYONE | 2017-03-28
Make figure showing discrepancy between the two models | EVERYONE
rough draft of interim report | EVERYONE
Email Bob with preliminary results and request real data for model confrontation | ????
Deliery of interim report on analysis | EVERYONE | 2017-04-04
Confront Bob's constant flow model with real data and summarize findings | Daniel, Nick, Atefeh | 2017-04-11
Confront new variable flow model with real data and summarize findings | Abby, Katie, Nathan
Quantify discrepancy between the two models with REAL DATA | EVERYONE | 2017-04-18
Make figure showing discrepancy between the two models WITH REAL DATA | EVERYONE
work on final report | EVERYONE
Rough draft of final report due | EVERYONE | 2017-04-25
Delivery of final report on analysis | EVERYONE | 2017-05-02